## Sheet1
Start Date | End Date | Topics | Status
2024-07-17 | 2024-07-17 | Understand Defination | completed
2024-07-17 | 2024-07-18 | Design author(Normal User) panel
2024-07-18 | 2024-07-19 | Design Admin panel
2024-07-22 | 2024-07-22 | Design Database and tables
2024-07-22 | 2024-07-22 | Admin login
2024-07-22 | 2024-07-23 | Manage blog categories(Add,update,delete,view)
2024-07-23 | 2024-07-25 | functionality of add,view,edit,delete blog for admin
2024-07-25 | 2024-07-25 | Add admin profile(update)
2024-07-26 | 2024-07-26 | Functionality of login and register
2024-07-26 | 2024-07-29 | functionality of add,view,edit,delete blog for author
2024-07-29 | 2024-07-29 | functionality of published/unpublished blog (admin side)
2024-07-30 | 2024-07-30 | Functionality of View published blogs page
2024-07-30 | 2024-07-30 | Functionality of single blog page
2024-07-30 | 2024-07-31 | Functionality of recent post
2024-07-31 | 2024-07-31 | functionality of search
2024-07-31 | 2024-08-01 | functionality of author profile(edit,delete)
2024-08-01 | 2024-08-01 | Add pagination
2024-08-01 | 2024-08-01 | Functionality of View user(admin side)
2024-08-01 | 2024-08-01 | Add logout
I will work with the upper topic which will require this topic |  | Add appropriate validation in form
User email functionality when required